## MSDS 460 Term Project Timeline
Category | Task | Start Date | Duration | End Date | Status | Comments
| Conduct Research About Topic Options | 2023-07-12 | 7 | 2023-07-19 | Complete
| Term Paper Check-In 1 | 2023-07-20 | 3 | 2023-07-23 | In Progress
| Solving The Problem (In Python) | 2023-07-20 | 24 | 2023-08-13 | Not Started
| Term Paper Check-In 2 | 2023-07-31 | 6 | 2023-08-06 | Not Started
| Write the Term Project Report | 2023-08-14 | 6 | 2023-08-20 | Not Started
| Create Resources (i.e. PowerPoint) Necessary for Video Presentation | 2023-08-14 | 6 | 2023-08-20 | Not Started
| Create the Term Project Video Presentation | 2023-08-21 | 5 | 2023-08-26 | Not Started